| - Ethical and professional aspects |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| I.1.1. | Supporting lifelong development of researchers (in particular, doctoral candidates and early-stage researchers) – action No. 1 | Coordinating unit: Interdisciplinary Doctoral School Implementing units: Interdisciplinary Doctoral School, Centre for Innovation and Entrepreneurship, E-Learning Centre, Computing & Information Services Centre, Multimedia Centre, Language Centre | Development of a tool to promote and communicate development opportunities available for doctoral candidates. The tool will provide information on training courses, conferences, grant schemes, research projects, and advisory services in entrepreneurship, technology transfer, intellectual property protection, and other areas. | development of a tool | Q1 2026 | I. 2.; I.7.; I.8.; Further gaps identified: III.23.; III.28.; IV.36.; IV.38.; IV.39.; IV.40.; |
| I.1.2. | Supporting lifelong development of researchers (in particular, doctoral candidates and early-stage researchers) – action No. 2 | Coordinating unit: Centre for Innovation and Entrepreneurship Implementing units: Centre for Innovation and Entrepreneurship, Interdisciplinary Doctoral School, Careers Office, Library | Design and development of multimedia training materials for doctoral candidates and early-stage researchers, focusing on practical knowledge in the areas of entrepreneurship, intellectual property rights, copyright, and the commercialisation of research results. The materials will be built around real-world case studies of successful innovation-driven companies. | number of developed multimedia training materials | Q1 2026-Q4 2027 | I. 2.; I.7.; I.8.; Further gaps identified: III.23.; III.28.; IV.36.; IV.38.; IV.39.; IV.40.; |
| I.1.3. | Supporting lifelong development of researchers (in particular, doctoral candidates and early-stage researchers) – action No. 3 | Coordinating unit: Research Support Centre Implementing units: Research Support Centre, Interdisciplinary Doctoral School, Careers Office, Library | Design and development of multimedia training materials for doctoral candidates and early-stage researchers, highlighting opportunities for academic career development, CV building for researchers, ethics (research career planning, funding acquisition, and meaningful academic engagement, success stories). | number of developed multimedia training materials | Q1 2026-Q4 2027 | I. 2.; I.7.; I.8.; Further gaps identified: III.23.; III.28.; IV.36.; IV.38.; IV.39.; IV.40.; |
| I.1.4. | Supporting lifelong development of researchers (in particular, doctoral candidates and early-stage researchers) – action No. 4 | Coordinating unit: Centre for Teaching and Learning Implementing unit: Centre for Teaching and Learning | Design and development of multimedia training materials for early-stage researchers on modern teaching and learning methods. | number of developed multimedia training materials | Q1 2026-Q4 2027 | I. 2.; I.7.; I.8.; Further gaps identified: III.23.; III.28.; IV.36.; IV.38.; IV.39.; IV.40.; |
| I.1.5. | Supporting lifelong development of researchers (in particular, doctoral candidates and early-stage researchers) – action No. 5 | Coordinating unit: Careers Office Implementing units: Careers Office, Interdisciplinary Doctoral School | Acquisition of a software licence enabling analysis of individual behavioural styles of doctoral candidates. This measure aims to support the development of personalised academic career development pathways by identifying natural predispositions and competencies of doctoral candidates at different stages in their research careers. | acquisition of a licence, number of performed analysis and consultations | Q1 2026 | I. 2.; I.7.; I.8.; Further gaps identified: III.23.; III.28.; IV.36.; IV.38.; IV.39.; IV.40.; |
| I.2.1. | Enhancing activities promoting research achievement and cooperation with TUL external environment - action No. 1 | Coordinating unit: Media and Communications Office Implementing units: Media and Communications Office, Research Support Centre, Computing & Information Services Centre, Press Officer, Faculties, Discipline Councils | Strengthening cooperation between the Media and Communications Office and faculty leadership and enhancing the visibility and use of existing communication channels and tools for disseminating information about the research conducted at TUL. | number of activities | Q1 2026-Q4 2027 | I.8.; I.9.; |
| I.2.2. | Enhancing activities promoting research achievement and cooperation with TUL external environment - action No. 2 | Coordinating unit: Media and Communications Office Implementing units: Media and Communications Office, Research Support Centre, Computing & Information Services Centre, Press Officer, Faculties, Discipline Councils, Centre for Innovation and Entrepreneurship | Organisation of the Days of Scientific Disciplines to stimulate interdisciplinary cooperation and cooperation between field of science, intensify activities concerning acquisition of funding from external sources, and cooperation with the socio-economic environment. | number of organised events | Q1 2026-Q4 2027 | I.8.; I.9.; |
| I.2.3. | Enhancing activities promoting research achievement and cooperation with TUL external environment - action No. 3 | Coordinating unit: Media and Communications Office Implementing units: Media and Communications Office, Research Support Centre, Press Officer, Faculties, Discipline Councils | Regular meetings with local and national media, e.g., the organisation of a press breakfast held in connection with the Days of Scientific Discipline. The aim of these meetings is to promote research conducted at TUL to a broader audience. | number of organised events | Q1 2026-Q4 2027 | I.8.; I.9.; |
| I.3. | Developing TUL open science policy | Coordinating unit: Library Implementing units: Library, Research Support Centre, Computing & Information Services Centre | Preparation of materials underpinning an internal open science policy, especially: an institutional open access policy, regulations for the open data repository and for the repository of TUL publications. Verification of the proposed research data management plan to ensure compliance with NCN requirements. | prepared materials | Q2 2025-Q1 2026 |  |
| I.4.1. | Training concerning periodic evaluation of staff - action No. 1 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, Careers Office, E-Learning Centre, Multimedia Centre, Research Support Centre, Centre for Teaching and Learning | Training for supervisors who evaluate academic staff as well as those evaluating non-academic staff. The action will be continued for new supervisors. | number of individuals trained | Q3-Q4 2025 | I.11.; Further gaps identified: IV.38.; IV.39.; |
| I.4.2. | Training concerning periodic evaluation of staff - action No. 2 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, Careers Office, E-Learning Centre, Multimedia Centre, Research Support Centre, Centre for Teaching and Learning | Development of multimedia training materials for employees undergoing evaluation, explaining the conditions and criteria based on Ordinance No. 79/2021 of the Rector of TUL dated 16 December 2021 regarding the periodic evaluation of academic staff, and Ordinance No. 27/2024 of the Rector of TUL dated 16 July 2024 concerning the evaluation of non-academic staff at Lodz University of Technology. | developed multimedia materials, number of views | Q1 2026 | I.11.; Further gaps identified: IV.38.; IV.39.; |
| I.5.1. | Enhancing understanding regarding preventing and addressing discrimination and mobbing – action No.1 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, Careers Office, Legal Services, E-Learning Centre, Multimedia Centre | Conducting trainings for members of the Anti-Discrimination and Anti-Mobbing Committee on tools for preventing and responding to discrimination and mobbing, as well as procedures to follow in the event of such incidents. | number of trained participants | Q1 2026 | I.10.; Further gap identified: III.27.; |
| I.5.2. | Enhancing understanding regarding preventing and addressing discrimination and mobbing – action No.2 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, Careers Office, Legal Services, E-Learning Centre, Multimedia Centre | Design and development of multimedia training materials for employees including the management and new employees, on preventing and addressing discrimination and mobbing. | number of developed multimedia training materials, number of views | Webinar design and development: Q3-Q4 2026 Materials available from Q1 2027 | I.10.; Further gap identified: III.27.; |
| I.6. | Implementation and promotion of the Gender Equality Plan for Lodz University of Technology for the years 2025-2027 (GEP) | Coordinating and implementing unit: Team for Gender Equality Plan Implementing units: Team for Gender Equality Plan, Media and Communications Office | Conducting and facilitating the implementation of tasks outlined in the Gender Equality Plan, supporting equality measures at the university, and promoting gender equality awareness within the TUL community. | number of promotional activities per year, number of reports | Q3 2025-Q4 2027 | I.2.; I.10.; Further gap identified: III.27. |
| II. Recruitment and selection |  |  |  |  |  |  |
| II.1.1. | Development, standardisation, and evaluation of recruitment processes at TUL – action No. 1 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, Careers Office, Multimedia Centre, E-Learning Centre, Legal Services | Further development of multimedia training materials for members of selection committees, which will serve as a comprehensive guide to current regulations, forms, and recruitment procedures at Lodz University of Technology. The materials will also cover equality in recruitment and promote transparent communication with job applicants, including giving individual feedback. | number of developed multimedia materials | Q3 2025 | II.12.; II.13.; II.14.; II.15.; II.16.; II.17.; II.19.; II.20.; II.21.; Further gap identified: III.28 |
| II.1.2. | Development, standardisation, and evaluation of recruitment processes at TUL – action No. 2 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, Careers Office, Multimedia Centre, E-Learning Centre, Legal Services | Introduction of a standard job advertisement template for non-academic staff recruitment. | standard template | Q3 2025 | II.12.; II.13.; II.14.; II.15.; II.16.; II.17.; II.19.; II.20.; II.21.; Further gap identified: III.28 |
| III. Working conditions |  |  |  |  |  |  |
| III.1.1. | Strengthening intercultural integration of doctoral candidates and researchers – action No. 1 | Coordinating unit: Interdisciplinary Doctoral School Implementing units: Interdisciplinary Doctoral School, International Cooperation Centre, Multimedia Centre, Media and Communications Office | Design and development of a series of video materials presenting cultural similarities and differences between Poland and the countries of origin of doctoral candidates (as set out in GEP 2.23 and STER NAWA). | number of video materials, number of views | Q2 2025-Q4 2026 | III.24.; III.27.; III.29.; Further gap identified: I.10.; |
| III.1.2. | Strengthening intercultural integration of doctoral candidates and researchers – action No. 2 | Coordinating unit: Interdisciplinary Doctoral School Implementing units: Interdisciplinary Doctoral School, International Cooperation Centre, Careers Office, Team for GEP | Organization of events supporting the intercultural integration of doctoral candidates, as envisioned in the Gender Equality Plan and the STER NAWA, including: - Diversity Day, organized as open networking meetings within an international group; - Intercultural workshops for doctoral candidates and research supervisors, aimed at promoting openness, tolerance, and mutual respect. | number of organized events | Q1 2026 - Q4 2027 | III.24.; III.27.; III.29.; Further gap identified: I.10.; |
| III.2. | Developing recommendations for preparing infrastructure proposals | Coordinating unit: Research Support Centre Implementing unit: Research Support Centre | Developing recommendations for preparing infrastructure proposals submitted to the Ministry of Science and Higher Education, in cooperation with individuals experienced in evaluating such proposals at the ministerial level. | developed document | Q2-Q3 2025, updated annually | III.24.; III.28. |
| III.3. | Kicking off TUL participation in the regional network NAWA-EURAXESS | Coordinating unit: Research Support Centre Implementing units: Research Support Centre, International Cooperation Centre | Developing a long-term strategy to attract and support foreign researchers, doctoral candidates, and their families. This initiative is carried out in cooperation with regional universities as part of the Lodzkie for International Researchers project. The project focuses on strengthening administrative competence, sharing best practices, and creating tools to support employment and the residence legalization processes. Partners also plan to expand the support network, foster integration within the scientific community through matchmaking meetings and newsletter and develop a joint strategy for the coming years. | Number of training sessions, number of project participants (in line with the project proposal) | Q4 2025-Q4 2027 | III.25.; III.28.; Further gap identified: II.18.; |
| III.4. | Developing a draft ordinance on international mobility of TUL staff, doctoral candidates, and students | Coordinating unit: International Cooperation Centre Implementing units: International Cooperation Centre, Financial/Accounting services, Human Capital Management Centre, Research Support Centre, Legal Services | Preparation of internal regulations governing international travel of TUL staff, doctoral candidates, and students, including standardised document templates. The regulations will define procedures for organising foreign travel, payment of travel-related expenses, insurance coverage, and the rules for advance payments and post-travel settlements. | draft ordinance | Q2-Q4 2025 | III.28.; III.29.; III.33.; Further gap identified: I.8.; |
| III.5. | Development of transparent rules for using university research infrastructure | Coordinating unit: Research Support Centre Implementing units: Research Support Centre, Centre for Innovation and Entrepreneurship, Skryba system Group | Development of an electronic register of research infrastructure and transparent rules for its use by TUL units and external stakeholders. | Module and search engine for the register of research infrastructure and amendment of Regulations for the use of TUL research infrastructure | Q4 2026 | III.23.; III.24.; |
| III.6.1. | Streamlining of administrative processes – action No.1 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, EZD Working Group, Computing & Information Services Centre | Ongoing development of the TETA ME employee system, through which, among others, leave is granted, and PIT and payroll information is provided. Additionally, continuous efforts are made to standardise, digitise, and simplify document circulation procedures, including through the EZD (Electronic Document Management) system. | number of the new functionalities and procedures | Q1 2025- Q4 2027 | III.24. |
| III.6.2. | Streamlining of administrative processes – action No.2 | Coordinating unit: Human Capital Management Centre Implementing units: Human Capital Management Centre, EZD Working Group, Computing & Information Services Centre | Improving IT competence for using university software systems through onboarding training for new employees and for employees returning after long periods of absence, e.g., after sick leave, maternity leave, and parental leave. | number of training participants | Q1 2025- Q4 2027 | III.24. |
| III.7. | Adaptation of building infrastructure for people with disabilities | Coordinating unit: Chancellor Implementing units: Chancellor, Office for People with Disabilities, Occupational Health and Safety Office | Continuation of measures to improve architectural accessibility of buildings. | number of adaptations completed | Q1 2025-Q4 2027 | III.24.; Further gap identified: I.10.; |
| IV. Training and development |  |  |  |  |  |  |
| IV.1. | Development and pilot implementation of a mentoring program | Coordinating unit: Careers Office Implementing units: Careers Office, Research Support Centre, Centre for Teaching and Learning, Centre for Innovation and Entrepreneurship, Interdisciplinary Doctoral School, Media and Communications Office | Development and pilot implementation of an internal mentoring program for early-stage researchers, focusing on scientific mentorship and academic entrepreneurship. Its goal is to help R1/R2 researchers build competence in areas such as grant acquisition, patenting, scientific publishing, teaching, and research commercialization. | formulating the program, carrying out pilot implementation | Formulation of the program by the end of Q4 2026 Pilot implementation in 2027 | IV.36.; IV.40.; Further gap identified: III.28.; |
| IV.2. | Evaluation of TUL Training programmes | Coordinating unit: Careers Office Implementing units: Careers Office, Centre for Teaching and Learning, Careers Office, E-Learning Centre | Develop a questionnaire to collect opinions and information on the expectations of trainees and recommend its use for evaluating training programs implemented at TUL. | developing an evaluation questionnaire, recommendation to conduct training evaluation | Q1 2027 | IV.39 |
| IV.3. | Intensifying scientific cooperation within European Consortium of Innovative Universities and advancing citizen science in research | Coordinating unit: Research Support Centre Implementing units: Research Support Centre, Faculty of Organization and Management - ECIU Research Field Coordinator - Citizen Science, International Cooperation Centre | Intensifying efforts to strengthen scientific cooperation within the ECIU consortium, including the development of interdisciplinary and between-fields-of-science research groups focused on sustainable development and social responsibility of universities. Activities supporting the integration of citizen science into research will also be undertaken. | number of activities | Q1 2025-Q4 2027 | IV. Further gaps identified: I.9; III.23;III.28; |
| IV.4. | Review of the industrial internship procedure | Coordinating unit: University Office for Development Implementing unit: University Office for Development | Updating the industrial internship procedure, including the internship application process, agreement signing, and required documentation. Revisions will also address the rules governing participation in the internship. | updated document | Q4 2026 | IV. 38.; Further gaps identified: III.28.; III. 29.; |